## Page_1
1. Agile User Story Template
Version: 1.0 |  |  | Date: 18-02-2019
User Story ID | As a <type of user> | I want to <perform some task> | so that I can <achieve some goal>
1 | Unregistered User | Create an account | Deny access to unauthorized personnel
2 | Registered User | Set the network interface for server | Allow the server to connect with clients
3 | Registered User | Visit the index page | Administer the Netdog server
4 | Registered User | Execute a command | Execute commands on all specified clients
5 | Registered User | Select subset of clients | Command executes only on specific machines
6 | Registered User | View Docs | Learn more about Netdog
7 | Registered User | Broadcast file | Broadcast a file to all of the client machines
8 | Registered User | Shutdown, Suspend shortcuts | Easy power management of clients
9 | Registered User | Monitor health of clients | Find if all clients are working correctly
10 | Registered User | See Netdog status | Find issues regarding working of Netdog
11 | Unregistered User | Install Netdog | Setup Netdog without hassle
Approval by Guide

## Page_2
2. PRODUCT BACKLOG
*To be planned before sprint starts
Version: 1.0 | [6 empty] | Date: 07/03/2019
User Story ID | Priority <High/Medium/low> | Story Points | Size (Hours) | Total | Sprint <#> | Status <Planned/In progress/done> | Release Date | Release Goal
1 | Medium | 6 | 2 | 2 | 1 | Done | 2019-03-07 | Deny access to unauthorized personnel
2 | Medium | 6 | 2 | 4 | 1 | Done | 2019-03-07 | Allow the server to connect with clients
3 | Medium | 7 | 5 | 9 | 1 | Done | 2019-03-07 | Administer the Netdog server
4 | Medium | 4 | 3 | 12 | 1 | Done | 2019-04-10 | Execute commands on all specified clients
5 | Medium | 5 | 4 | 16 | 1 | Done | 2019-04-11 | Command executes only on specific machines
6 | Medium | 6 | 7 | 23 | 1 | Done | 2019-04-12 | Administer the Netdog server
7 | Medium | 8 | 8 | 31 | 1 | Done | 2019-04-13 | Broadcast a file to all of the client machines
8 | Medium | 6 | 7 | 36 | 2 | Done | 2019-04-21 | Easy power management of clients
9 | Medium | 6 | 7 | 41 | 2 | Done | 2019-04-21 | Find if all clients are working correctly
10 | Medium | 6 | 7 | 43 | 3 | Done | 2019-05-16 | Find issues regarding working of Netdog
11 | High | 8 | 8 | 48 | 3 | Done | 2019-05-16 | Setup Netdog without hassle
* Story points out of 10 may be assigned based on priority
|  |  | Approval by Product owner |  |  |  | Approval by Guide

## Page_3
3. Agile Project Plan
*To be planned before sprint starts
| Version: 1.0 |  |  |  | Date: 16/05/2019
Overall Progress: 100%
User Story ID | Task Name | Responsible | Start date | End date | Days | Status (to be filled by Scrum Master)
| Sprint 1 | Aswin Babu K | 2019-02-07 | 2019-03-07 | 28 | Complete
1 | Switch to flask | Aswin Babu K | 2019-02-07 | 2019-03-07 | 28 | Complete
1 | Create account | Aswin Babu K | 2019-02-08 | 2019-03-08 | 28 | Complete
1 | Separate process for web server | Aswin Babu K | 2019-02-09 | 2019-03-09 | 28 | Complete
1 | Network interface selection page | Aswin Babu K | 2019-02-10 | 2019-03-10 | 28 | Complete
1 | Setup cookies | Aswin Babu K | 2019-02-11 | 2019-03-11 | 28 | Complete
1 | Create login page | Aswin Babu K | 2019-02-12 | 2019-03-12 | 28 | Complete
1 | Create password creation page | Aswin Babu K | 2019-02-13 | 2019-03-13 | 28 | Complete
1 | First time run screen | Aswin Babu K | 2019-02-14 | 2019-03-14 | 28 | Complete
2 | Let nodes to update IP | Aswin Babu K | 2019-02-15 | 2019-03-15 | 28 | Complete
2 | Update client side last_known_address | Aswin Babu K | 2019-02-16 | 2019-03-16 | 28 | Complete
2 | Fix update nodes overwriting dict | Aswin Babu K | 2019-02-17 | 2019-03-17 | 28 | Complete
2 | Create beacon system | Aswin Babu K | 2019-02-18 | 2019-03-18 | 28 | Complete
3 | Create beacon DB | Aswin Babu K | 2019-02-19 | 2019-03-19 | 28 | Complete
3 | Beacon DB cleanup thread | Aswin Babu K | 2019-02-20 | 2019-03-20 | 28 | Complete
| Sprint 2 | Aswin Babu K | 2019-02-07 | 2019-04-07 | 59 | Complete
4 | Create Execute command UI | Aswin Babu K | 2019-03-07 | 2019-04-08 | 32 | Complete
4 | Create function to get active clients | Aswin Babu K | 2019-03-08 | 2019-04-08 | 31 | Complete
5 | Implement target clients UI | Aswin Babu K | 2019-03-09 | 2019-04-09 | 31 | Complete
5 | Implement checkbox in target clients | Aswin Babu K | 2019-03-10 | 2019-04-10 | 31 | Complete
6 | Create documentation in Github | Aswin Babu K | 2019-03-11 | 2019-04-11 | 31 | Complete
6 | Link documentation to web UI | Aswin Babu K | 2019-03-12 | 2019-04-12 | 31 | Complete
7 | Implement broadcast function | Aswin Babu K | 2019-03-13 | 2019-04-13 | 31 | Complete
7 | Implement broadcast UI | Aswin Babu K | 2019-03-14 | 2019-04-14 | 31 | Complete
8 | Implement shutdown shortcut | Aswin Babu K | 2019-03-15 | 2019-04-15 | 31 | Complete
8 | Implement Suspend shortcut | Aswin Babu K | 2019-03-16 | 2019-04-16 | 31 | Complete
| Sprint 3 | Aswin Babu K | 2019-04-07 | 2019-05-07 | 30 | Complete
9 | Configure conky to get required stats | Aswin Babu K | 2019-04-07 | 2019-05-07 | 30 | Complete
9 | Send output of conky through beacon | Aswin Babu K | 2019-04-08 | 2019-05-08 | 30 | Complete
9 | Implement statistics UI | Aswin Babu K | 2019-04-09 | 2019-05-09 | 30 | Complete
10 | Complete logs | Aswin Babu K | 2019-04-10 | 2019-05-10 | 30 | Complete
11 | Create deployer | Aswin Babu K | 2019-04-11 | 2019-05-11 | 30 | Complete
11 | Create deployer | Aswin Babu K | 2019-04-11 | 2019-05-11 | 30 | Complete

## Page_4
5. Database & UI Design
*To be planned before sprint starts
Sprint <#>
Version No.
Sprint Dates: <Month> <DD> - <Month> <DD>, <YYYY>
<Include Database design and User interface design >

## Page_5
6. Testing and Validation
Version: 1.0 |  | Sprint#: 1
Test # | Date | Action | Expected Results | Actual Results | Pass? <Yes/No>
1 | 2016-03-06 | Logging in | Should get to home screen | User directed to different page | Yes
2 | 2016-03-12 | Signing up for webinar | Get confirmation email | Confirmation email received | No
3 | 2016-03-20 | Click magnifying glass | Whole page gets bigger | Text changes sizes | Yes
4 | 2016-04-01 | Click blog post hero image | Go to blog post | Go to blog post
Approval by Scrum Master