## Page_1
1. Agile User Story Template
Version: 1.0 |  |  | Date: 18-02-2019
User Story ID | As a <type of user> | I want to <perform some task> | so that I can <achieve some goal>
1 | Unregistered User | Create an account | Deny access to unauthorized personnel
2 | Registered User | Set the network interface for server | Allow the server to connect with clients
3 | Registered User | Visit the index page | Administer the Netdog server
4 | Registered User | Execute a command | Execute commands on all specified clients
5 | Registered User | Select subset of clients | Command executes only on specific machines
6 | Registered User | Execute a command | Administer the Netdog server
7 | Registered User | Broadcast file | Broadcast a file to all of the client machines
Approval by Guide

## Page_2
2. PRODUCT BACKLOG
*To be planned before sprint starts
Version: 1.0 | [6 empty] | Date:
User Story ID | Priority <High/Medium/low> | Story Points | Size (Hours) | Total | Sprint <#> | Status <Planned/In progress/done> | Release Date | Release Goal
1 | Medium | 6 | 2 | 2 | 1 | Planned | 2019-03-07 | Deny access to unauthorized personnel
2 | Medium | 6 | 2 | 4 | 1 | Planned | 2019-03-08 | Allow the server to connect with clients
3 | Medium | 7 | 5 | 9 | 1 | Planned | 2019-03-09 | Administer the Netdog server
4 | Medium | 4 | 3 | 12 | 1 | Planned | 2019-03-10 | Execute commands on all specified clients
5 | Medium | 5 | 4 | 16 | 1 | Planned | 2019-03-11 | Command executes only on specific machines
6 | Medium | 6 | 7 | 23 | 1 | Planned | 2019-03-12 | Administer the Netdog server
7 | Medium | 8 | 8 | 31 | 1 | Planned | 2019-03-13 | Broadcast a file to all of the client machines
* Story points out of 10 may be assigned based on priority
|  |  | Approval by Product owner |  |  |  | Approval by Guide

## Page_3
3. Agile Project Plan
*To be planned before sprint starts
| Version: 1.0 |  |  |  | Date:
Overall Progress: 20%
User Story ID | Task Name | Responsible | Start date | End date | Days | Status (to be filled by Scrum Master)
| Sprint 1 | Alex B. |  |  | 0 | Complete
1 | Task 1 | Frank C. |  |  | 0 | Complete
1 | Task 2 | Jacob S. |  |  | 0 | Complete
2 | Task 3 | Jacob S. |  |  | 0 | Overdue
| Sprint 2 | Jacob S. |  |  | 0 | In progress
3 | Task 4 | Alex B. |  |  | 0 | In progress
3 | Task 5 | Frank C. |  |  | 0 | Not started
3 | Task 6 | Shari W. |  |  | 0 | Not started
Approval by Scrum Master

## Page_4
5. Database & UI Design
*To be planned before sprint starts
Sprint <#>
Version No.
Sprint Dates: <Month> <DD> - <Month> <DD>, <YYYY>
<Include Database design and User interface design >

## Page_5
6. Testing and Validation
Version: 1.0 |  | Sprint#: 1
Test # | Date | Action | Expected Results | Actual Results | Pass? <Yes/No>
1 | 2016-03-06 | Logging in | Should get to home screen | User directed to different page | Yes
2 | 2016-03-12 | Signing up for webinar | Get confirmation email | Confirmation email received | No
3 | 2016-03-20 | Click magnifying glass | Whole page gets bigger | Text changes sizes | Yes
4 | 2016-04-01 | Click blog post hero image | Go to blog post | Go to blog post
Approval by Scrum Master