## Page_2
2.Agile User Story Template
Version: 1.0			Date: 07-09-2018

User Story ID	As a <type of user>	I want to <perform some task>	so that <achieve some goal>
1	admin	Shutdown all computers on the network remotely	Computers can be turned off without physically going to each machine
2	admin	Execute script remotely on the machine	Administrative tasks such as software installation can be done on all machines on the network at once
3	admin	Copy files to remote machines	Files can be copied to all machines on the network without user intervention

		Approval by Guide

## Page_3
3. PRODUCT BACKLOG
		*To be planned before sprint starts
Version: 1.0					Date: 07-09-2018

User Story ID	Priority	Story Points	Size (Hours)	Total	Sprint <#>	Status	Release Date	Release Goal
1	High	6	8	8	1	In Progress	20-09-2018	Shutdown computers on the network remotely
2	High	3	4	12	2	Planned	30-09-2018	Execute tasks on all machines at once
3	Medium	10	4	16	3	Planned	10-10-2018	Copy files to all machines without 3rd party protocol

	* Story points out of 10 may be assigned based on priority

			Approval by Product owner				Approval by Guide

## Page_4
	4.Agile Project Plan
		*To be planned before sprint starts
	Version: 1.0				Date: 07-09-2018
	Overall Progress: 20%

User Story ID	Task Name	Responsible	Start date	End date	Days	Status (to be filled by Scrum Master)
	Sprint 1	Aswin Babu K	9/1	9/14	13
1	Initialize system	Aswin Babu K	9/1	9/7	6
1	Scan for hosts on the network	Aswin Babu K	9/7	9/12	5
1	Handle the received data	Aswin Babu K	9/12	9/14	2
	Sprint 2	Aswin Babu K			0
2		Aswin Babu K			0
2		Aswin Babu K			0
2		Aswin Babu K			0
	Sprint 3	Aswin Babu K
3		Aswin Babu K
3		Aswin Babu K
3		Aswin Babu K

						Approval by Scrum Master

## Page_5
5.SPRINT BACKLOG (PLANNING)
					*To be planned before sprint starts
Sprint: #					Date:
Version: 1.0
Sprint Dates: <Month> <DD> - <Month> <DD>, <YYYY>
Sprint Goal:

Backlog Item	Story Points	Responsible	Status and Completion date	Original Estimate in hours	Day 1 <Date>	Day 2 <Date>	Day 3 <Date>	Day 4 <Date>	Day 5 <Date>	Day 6 <Date>	Day 7 <Date>	Day 8 <Date>
User Story #1	8				Hours	Hours	Hours	Hours	Hours	Hours	Hours	Hours
<Task >		<Developer Name>	Planned, 12/09/2018	2	1	1	0	0				0
Task				4	2	0	2	0				1
Task				1	0.5	0	3	0				0
Task				1	1	2	3	1				0
User Story #2	1
Task				3	3	0.5	0.5	0				0
Task				3	5	5	1	1				1
Task				2	2	5	0	1				0
Task				5	5	9	5	1				0
User Story #3	5
Task				8	6	0	0	0				0
Task				3	1	3	3	3				0
Task				1.5	1	0.5	0.5	1				1
Task				2	0.5	0	0	0				0
User Story #4	8
Total				35.5	28	26	18	8				3

Remaining Story Points:
					Signature of Scrum Master

## Page_6
6. SPRINT BACKLOG (ACTUAL)
					*To be filed at the end of each sprint
Sprint: #					Date:
Version: 1.0
Sprint Dates: <Month> <DD> - <Month> <DD>, <YYYY>
Sprint Goal:

Backlog Item	Story Points	Responsible	Status and Completion date	Original Estimate in hours	Day 1 <Date>	Day 2 <Date>	Day 3 <Date>	Day 4 <Date>	Day 5 <Date>	Day 6 <Date>	Day 7 <Date>	Day 8 <Date>	Done <Y/N> to be filled by Scrum Master
User Story #1	8				Hours	Hours	Hours	Hours	Hours	Hours	Hours	Hours
<Task >		<Developer Name>	Completed, 12/09/2018	2	1	1	0	0				0	Y
Task				4	2	0	2	0				1	N
Task				1	0.5	0	3	0				0	N
Task				1	1	2	3	1				0	N
User Story #2	1
Task				3	3	0.5	0.5	0				0
Task				3	5	5	1	1				1
Task				2	2	5	0	1				0
Task				5	5	9	5	1				0
User Story #3	5
Task				8	6	0	0	0				0
Task				3	1	3	3	3				0
Task				1.5	1	0.5	0.5	1				1
Task				2	0.5	0	0	0				0
User Story #4	8
Total				35.5	28	26	18	8				3

Remaining Story Points:
					Signature of Scrum Master

## Page_7
7. Database & UI Design

*To be planned before sprint starts

Sprint <#>
Version No.
Sprint Dates: <Month> <DD> - <Month> <DD>, <YYYY>

<Include Database design and User interface design >

## Page_8
8. Testing and Validation

Version: 1.0		Sprint#: 1

Test #	Date	Action	Expected Results	Actual Results	Pass? <Yes/No>
1	6-Mar	Logging in	Should get to home screen	User directed to different page	Yes
2	12-Mar	Signing up for webinar	Get confirmation email	Confirmation email received	No
3	20-Mar	Click magnifying glass	Whole page gets bigger	Text changes sizes	Yes
4	1-Apr	Click blog post hero image	Go to blog post	Go to blog post

					Approval by Scrum Master