## Page_2
2.Agile User Story Template
Version: 1.0			Date:

User Story ID	As a <type of user>	I want to <perform some task>	so that I can <achieve some goal>
1	Registered User	Change my password	Keep my account safe
2	Website Visitor	Subsribe to the mailing list for a product	Get the product updates through mail
3	Admin	disable user	Prevent unauthorized users

		Approval by Guide

## Page_3
3. PRODUCT BACKLOG
		*To be planned before sprint starts
Version: 1.0					Date:

User Story ID	Priority <High/Medium/low>	Story Points	Size (Hours)	Total	Sprint <#>	Status <Planned/In progress/done>	Release Date	Release Goal
1	Medium	6	2	2	1	Planned	5/9/2018	Registered User can change Passwords
2	Low	3	2	4	1
3	High	10	5	9	2

	* Story points out of 10 may be assigned based on priority

			Approval by Product owner				Approval by Guide

## Page_4
	4.Agile Project Plan
		*To be planned before sprint starts
	Version: 1.0				Date:
	Overall Progress: 20%

User Story ID	Task Name	Responsible	Start date	End date	Days	Status (to be filled by Scrum Master)
	Sprint 1	Alex B.			0	Complete
1	Task 1	Frank C.			0	Complete
1	Task 2	Jacob S.			0	Complete
2	Task 3	Jacob S.			0	Overdue
	Sprint 2	Jacob S.			0	In progress
3	Task 4	Alex B.			0	In progress
3	Task 5	Frank C.			0	Not started
3	Task 6	Shari W.			0	Not started

						Approval by Scrum Master

## Page_5
5.SPRINT BACKLOG (PLANNING)
					*To be planned before sprint starts
Sprint: #					Date:
Version: 1.0
Sprint Dates: <Month> <DD> - <Month> <DD>, <YYYY>
Sprint Goal:

Backlog Item	Story Points	Responsible	Status and Completion date	Original Estimate in hours	Day 1 <Date>	Day 2 <Date>	Day 3 <Date>	Day 4 <Date>	Day 5 <Date>	Day 6 <Date>	Day 7 <Date>	Day 8 <Date>
User Story #1	8				Hours	Hours	Hours	Hours	Hours	Hours	Hours	Hours
<Task >		<Developer Name>	Planned, 12/09/2018	2	1	1	0	0				0
Task				4	2	0	2	0				1
Task				1	0.5	0	3	0				0
Task				1	1	2	3	1				0
User Story #2	1
Task				3	3	0.5	0.5	0				0
Task				3	5	5	1	1				1
Task				2	2	5	0	1				0
Task				5	5	9	5	1				0
User Story #3	5
Task				8	6	0	0	0				0
Task				3	1	3	3	3				0
Task				1.5	1	0.5	0.5	1				1
Task				2	0.5	0	0	0				0
User Story #4	8
Total				35.5	28	26	18	8				3

Remaining Story Points:
					Signature of Scrum Master

## Page_6
6. SPRINT BACKLOG (ACTUAL)
					*To be filed at the end of each sprint
Sprint: #					Date:
Version: 1.0
Sprint Dates: <Month> <DD> - <Month> <DD>, <YYYY>
Sprint Goal:

Backlog Item	Story Points	Responsible	Status and Completion date	Original Estimate in hours	Day 1 <Date>	Day 2 <Date>	Day 3 <Date>	Day 4 <Date>	Day 5 <Date>	Day 6 <Date>	Day 7 <Date>	Day 8 <Date>	Done <Y/N> to be filled by Scrum Master
User Story #1	8				Hours	Hours	Hours	Hours	Hours	Hours	Hours	Hours
<Task >		<Developer Name>	Completed, 12/09/2018	2	1	1	0	0				0	Y
Task				4	2	0	2	0				1	N
Task				1	0.5	0	3	0				0	N
Task				1	1	2	3	1				0	N
User Story #2	1
Task				3	3	0.5	0.5	0				0
Task				3	5	5	1	1				1
Task				2	2	5	0	1				0
Task				5	5	9	5	1				0
User Story #3	5
Task				8	6	0	0	0				0
Task				3	1	3	3	3				0
Task				1.5	1	0.5	0.5	1				1
Task				2	0.5	0	0	0				0
User Story #4	8
Total				35.5	28	26	18	8				3

Remaining Story Points:
					Signature of Scrum Master

## Page_7
7. Database & UI Design

*To be planned before sprint starts

Sprint <#>
Version No.
Sprint Dates: <Month> <DD> - <Month> <DD>, <YYYY>

<Include Database design and User interface design >

## Page_8
8. Testing and Validation

Version: 1.0		Sprint#: 1

Test #	Date	Action	Expected Results	Actual Results	Pass? <Yes/No>
1	6-Mar	Logging in	Should get to home screen	User directed to different page	Yes
2	12-Mar	Signing up for webinar	Get confirmation email	Confirmation email received	No
3	20-Mar	Click magnifying glass	Whole page gets bigger	Text changes sizes	Yes
4	1-Apr	Click blog post hero image	Go to blog post	Go to blog post

					Approval by Scrum Master